Interim report

Summary

During this period, the project made significant progress in consolidating the technical foundations needed to assess resilient harvest control rules in Chilean demersal crustacean fisheries, in line with the objectives set out in the original proposal. Progress has focused on three main areas. First, the most relevant sources of uncertainty for the stock assessments of the red squat lobster, yellow squat lobster, and nylon shrimp were identified and systematized. Second, an alternative stock assessment model for nylon shrimp was developed and analyzed, structured by age and incorporating spatial heterogeneity in length composition and maturity. Third, work has advanced on the construction of a preliminary portfolio of catch control rules, including both empirical and model-based rules. We reviewed and suggested minor changes to model-based harvest control rules based on the current management plan, with a view to their subsequent comparative evaluation under a management strategy evaluation approach. In parallel, the project engaged with relevant technical and institutional bodies, including the Technical and Scientific Committee and Management Committee for Demersal Crustaceans, the Undersecretariat of Fisheries and Aquaculture, and expert review spaces, which made it possible to compare criteria, strengthen the methodological approach, and align technical development with fishery management needs. Taken together, these advances indicate that the project has completed a key stage of conceptual, analytical, and institutional preparation, thereby laying a solid foundation for the next phase of implementation and comparing control rule performance across different uncertainty scenarios.

2.	Cambios del proyecto

a.	Indicar cambios menores que hayan hecho al proyecto y explicar por qué.

b.	Ojo: los cambios significativos requieren aprobación previa del Ocean Stewardship Fund.

No substantive changes were made to the general objectives or the scope of the project. During this stage, the work focused on strengthening the technical foundation of activities that were already included in the original proposal, especially in the review of sources of uncertainty for stock assessments, analysis of an alternative formulation for the nylon shrimp assessment, and structuring of a preliminary portfolio of harvest control rules. This emphasis was in response to the need to first consolidate the technical inputs that will allow for a more robust development of the next phase of the project, which is associated with the implementation of operating models and the comparative evaluation of control rules under uncertainty.

3.	Desafíos a.	Resumir qué dificultades han tenido y qué acciones tomaron para enfrentarlas.  One of the main challenges during the period was addressing the complexity and uncertainty that affect stock assessments and, by extension, the design of robust harvest control rules for demersal crustacean fisheries. The review carried out showed that these uncertainties are not limited to data variability but also involve biological, structural, observational, and spatial assumptions. In the case of nylon shrimp, additional specific challenges were identified, such as representing spatial heterogeneity of the stock, estimating fishing mortality, and the integrated interpretation of the resource status. To tackle these challenges, the project advanced in reviewing and analyzing an alternative assessment approach that is age-structured and spatially explicit for nylon shrimp, as well as in systematizing a preliminary portfolio of catch control rules that may later be evaluated under different uncertainty assumptions. Additionally, participation in technical meetings with committees, institutional counterparts, and expert review panels made it possible to gather relevant feedback and strengthen the adopted methodological approach.

4.	Comunicación y difusión a.	Contar qué actividades de difusión o outreach han realizado para compartir resultados. b.	Incluir URLs si corresponde. c.	Señalar también qué actividades de comunicación planean hacer más adelante.  During the period, various technical communication and institutional coordination activities were carried out, aimed at sharing project progress and gathering specialized feedback. In the next stage of the project, technical communication of progress and results is expected to continue with relevant sectoral actors, particularly through discussion instances with the Demersal Crustacean Scientific and Technical Committee, the Management Committee, and invited experts, in line with commitments from the original proposal. These instances made it possible to socialize the project’s approach, discuss proposals related to harvest control rules, and strengthen the link between the project's technical development and fisheries management needs. Up to this stage, project communication has been mainly targeted at technical, institutional, and management stakeholders directly involved with these fisheries.  In the next stage of the project, technical communication of progress and results is expected to continue with relevant sectoral actors, particularly through discussion instances with the Demersal Crustacean Scientific and Technical Committee, the Management Committee, and invited experts, in line with commitments from the original proposal. Likewise, the results of the comparative evaluation of control rules are expected to serve as the basis for technical recommendations aimed at strengthening management and closing existing gaps related to the MSC condition regarding harvest control rules. Additionally, there are plans to move towards scientific outreach products, including the future preparation of a scientific article for a specialized journal.

5.	Confidencialidad y redes sociales

a.	Decir si hay hallazgos que prefieren que el fondo no comparta públicamente, explicando por qué y por cuánto tiempo. b.	Responder si pueden etiquetarlos en publicaciones de redes sociales sobre el proyecto.

6.	Actividades futuras a.	Resumir qué actividades realizarán antes del próximo reporte.

In the next report, we will focus on deepening the benchmarking phase of harvest control rules under scenarios of uncertainty, using the technical foundation already developed during this stage. In particular, progress is expected in the implementation and conditioning of operative models, formalization of alternative productivity and observation scenarios, and comparison of the performance of current and alternative control rules using sustainability and fisheries performance indicators. Additionally, coordination with the Demersal Crustacean Scientific and Technical Committee, Management Committee, and invited experts will continue to strengthen the discussion of results and guide the formulation of final recommendations.

7.	Outputs y outcomes del proyecto

a.	Para cada acción del proyecto, llenar:

i.	número de acción

ii.	nombre de la acción

iii.	MSC PI(s)

iv.	output esperado

v.	outcome esperado

vi.	fecha de término

vii.	estado

viii.	outputs/outcomes logrados

ix.	si va atrasado, explicar razones y medidas tomadas.

En tu formulario aparecen estas 4 acciones:

b.	Nylon shrimp age-structured and spatial stock assessment model

c.	Resilient harvest control rules (HCR)

d.	Operating models for the Chilean crustaceans fishery units

e.	Workshop: Stakeholder Consultation and Final Recommendations

Action 1

Action number: 1

Action name: Nylon shrimp age-structured and spatial stock assessment model.

MSC PI(s): PI 1.2.4 – Stock assessment

Expected output: A computational code in ADMB, compiled and executable, for the stock assessment of nylon shrimp, capable of reading input data and estimating the main population parameters of the resource.

Expected outcome: A methodological and operational foundation that allows for a better representation of the dynamics of the nylon shrimp stock and supports a more robust interpretation of its status.

End date: 07/18/2025

Status: Completed

Outputs/outcomes achieved:

During this stage, the development, implementation, and analytical application of an age-structured and spatially explicit stock assessment formulation for nylon shrimp was completed. The work carried out made it possible to integrate long-term fishery biological information, assess the model’s fit to multiple data sources, and reconstruct the temporal dynamics of spawning biomass, recruitment, and fishing mortality. In addition, the retrospective stability of the assessment was examined and the stock status was interpreted in relation to biological reference points. Together, these results provide a solid technical basis to represent the dynamics of the resource and constitute a direct input for the next phase of the project, focused on the implementation of operational models and the comparative evaluation of harvest control rules.

If it is delayed, reasons and measures taken:

Not applicable